## Sprint Planning
GRANT APPLICATION SYSTEM
Sprint 1 - Planning & Setup
Sprint Planning |  | Project Architecture | Testing architecture | CI/CD pipeline architecture
Week 1 | Sprint 1 | 1. Setting up JIRA integration with slack & GitHub. 2. Architecture Design Discussions: Conducting discussions to outline the overall project architecture, considering frontend, backend, security, and database components. Defineing technology stacks and frameworks to be used. 3. Initial Environment Setup: Set up development environments for both frontend and backend teams. Configure version control systems and collaboration tools. | 1. Testing Strategy: Outline the overall testing strategy and objectives. Define the types of tests to be conducted: functional, non-functional, integration, security, etc. 2. Test Environment Setup: Establishing the initial testing environment mirroring the development setup. Configure necessary tools and testing frameworks. | 1. Assessment of DevOps Needs: Conducting an initial assessment of the project requirements for CI/CD integration. Identifying tools and technologies required for the pipeline setup. 2. Tool Selection and Setup: Research and select CI/CD tools (e.g., Jenkins, GitLab CI/CD, GitHub Actions) suitable for the project. Set up the basic infrastructure for the CI/CD pipeline.
2023-12-11
week 2
2023-12-18
Sprint 2 - Prototype Development / Test Planning & Preparation / Source Control & Basic CI Setup
week 3 | Sprint 2 | 1. Frontend Development: Begin developing the frontend UI prototypes using React.js/Vue.js or preferred frameworks. Design basic forms and user interfaces for data input. 2. Backend Setup: Establish the foundational backend infrastructure using Node.js/Django/Flask or chosen backend technologies. Create initial APIs to handle basic data transactions. | 1. Test Plan Creation: Develop a comprehensive test plan including scope, objectives, resources, and timelines. Identify testing priorities and critical areas. 2. Test Case Design Initiation: Begin designing initial test cases for basic functionalities and user interactions. Define test scenarios and edge cases to be covered. | 1. Source Control Integration: Integrate the project with a version control system (e.g., Git) and establish repositories. Set up branching strategies and policies. 2. Basic CI Configuration: Configure the initial build process in the CI system to trigger builds upon code commits. Implement basic build steps and tests for the codebase.
2023-12-25
week 4
2024-01-01
Sprint 3 - Detailed Functionality & Testing Setup / Test Case Design & Execution Start / Test Automation & Environment Configuration
Week 5 | sprint 3 | 1. Enhanced UI Development: Refine and expand the frontend UI to accommodate additional functionalities. Integrate user input validation for improved user experience. 2. Advanced Backend Logic: Develop more intricate backend logic for mapping user inputs to grant choices and handling special award applications. Begin setting up initial testing environments and frameworks (e.g., Jest for frontend, PyTest for backend). | 1.Test Case Development: Expand test case coverage to include more complex scenarios and integration points. Ensure traceability between test cases and requirements 2. Initial Test Execution: Start executing basic tests on developed functionalities. Log and track identified defects and issues. | 1. Test Automation Integration: Integrate testing frameworks (e.g., Jest, PyTest) into the CI pipeline for automated testing. Create test suites and scripts for automated tests. 2. Environment Configuration: Define and configure development, testing, and staging environments in the pipeline. Automate environment provisioning where possible.
2023-01-08
week 6
2023-01-15
Sprint 4 - Security Implementation & Database Setup / Security Testing & Test Data Management / Deployment Setup & Security Measures
week 7 | Sprint 4 | Security Measures: Implement basic security measures such as encryption protocols and authentication mechanisms. Perform initial security testing on data transmission and storage. Database Structure Setup: Design and implement the initial database structure using chosen databases (e.g., PostgreSQL, MongoDB). Set up database connections and ensure data integrity. | Security Testing Setup: Integrate security testing methodologies (e.g., penetration testing, vulnerability scanning) into the testing plan. Conduct initial security assessments. Test Data Preparation: Create realistic test data sets covering various scenarios. Ensure compliance with data privacy regulations and sensitivity considerations. | Deployment Configuration: Establish deployment configurations for various environments using deployment scripts or configuration files. Set up deployment stages and dependencies. Security Integration: Integrate security checks (e.g., code scanning, vulnerability assessment) into the pipeline. Implement security measures during the deployment process.
2023-01-22
week 8
2023-01-29
Sprint 5 - Refinement & Additional Features / Comprehensive Test Execution & Reporting / Integration Testing & Monitoring Setup
week 9 | sprint 5 | Refinement of UI/UX: Refine UI components based on user feedback and design principles. Optimize UI for responsiveness and user interaction. Additional Feature Development: Implement additional minor features based on evolving requirements. Enhance functionalities based on stakeholder inputs. | Comprehensive Test Execution: Execute a wider range of test cases covering functional and non-functional aspects. Perform regression testing on updated functionalities. Test Result Analysis & Reporting: Analyze test results and generate detailed test reports. Document findings, including pass/fail statuses, defects, and coverage metrics. | Integration Testing Configuration: Expand the CI/CD pipeline to include integration testing stages. Configure test environments for integration tests. Monitoring and Reporting Setup: Integrate monitoring tools (e.g., Prometheus, Grafana) for tracking pipeline performance. Set up reporting mechanisms for test results and pipeline metrics.
2023-02-05
week 10
2023-02-12
Sprint 6 - Finalization & Documentation Preparation / Refinement & Automation Integration / Continuous Improvement & Optimization
week 11 | sprint 6 | Finalization of Functionalities: Conduct thorough testing and bug fixing for existing features. Ensure all core functionalities meet requirements. Documentation Preparation: Start preparing user manuals, system documentation, and deployment guides. Outline documentation for API endpoints and database schema. | Test Case Refinement: Refine and update test cases based on previous executions and feedback. Ensure test cases reflect changes in the application. Automation Framework Integration: Start integrating automation frameworks (if not already done) for regression and repetitive tests. Develop scripts for automated test cases. | Pipeline Optimization: Fine-tune the CI/CD pipeline for performance improvements and faster feedback loops. Optimize build times and resource utilization. Process Automation: Automate additional processes like dependency management, artifact storage, and cleanup tasks within the pipeline.
2023-02-19
week 12
2023-02-26
Sprint 7 - Deployment Preparation & Integration / Continuous Testing & Optimization / Continuous Deployment & Rollback Strategies
week 13 | sprint 7 | Deployment Planning: Plan deployment strategies, including staging and production environments. Set up CI/CD pipelines for automated testing and deployment. Integration of Security & Scalability Measures: Strengthen security measures and implement scalability strategies in the architecture. Ensure systems are ready for scaling and handling increased traffic. | Continuous Integration/Continuous Deployment (CI/CD) Integration: Integrate testing into CI/CD pipelines for automated testing on code changes. Ensure automated tests run upon deployments. Testing Process Optimization: Optimize testing processes and methodologies based on learnings and efficiency gains. Fine-tune testing environments for better stability and speed. | Continuous Deployment Setup: Enable continuous deployment for the application in the pipeline. Implement automated deployments to staging and testing environments. Rollback Strategies: Establish rollback mechanisms and strategies in case of deployment failures. Test and validate rollback procedures.
2023-03-04
week 14
2023-03-11
Sprint 8 - Deployment & Post-Deployment Support / Final Testing & Documentation / Finalization & Documentation
week 15 | sprint 8 | System Deployment: Deploy the finalized system into the production environment. Monitor deployment and address immediate issues. Post-Deployment Support & Iterative Improvements: Provide ongoing support for any issues post-deployment. Initiate gathering feedback for future updates and enhancements. | Final Testing & Validation: Conduct final testing, focusing on critical areas and end-to-end scenarios. Ensure the system is stable and ready for deployment. Documentation & Knowledge Transfer: Prepare comprehensive documentation on testing processes, methodologies, and results. Facilitate knowledge transfer to support teams and stakeholders | Final Testing and Validation in Pipeline: Conduct final tests and validations within the CI/CD pipeline, ensuring readiness for production. Validate end-to-end deployment processes. Documentation & Knowledge Sharing: Create comprehensive documentation on CI/CD processes, setup, and best practices. Conduct knowledge sharing sessions for team members and stakeholders.
2023-03-18
week 16
2023-03-25

## Scrum workflow
Scrum Workflow
S No | Product backlog | Sprint planning | Sprint backlog | Sprint | Potentially shippable product | Sprint review | Retrospective
1 |  |  |  | Sprint 1
2 |  |  |  | Sprint 1
3 |  |  |  | Sprint 1
4
5
6
7
8

## Roles
Roles | Members | Sprint
Scrum Master | Honnesh Muppala | 1
Product owner | Moosa, Shyam | 1
Team members (Testing and Operations) | Chandan, Arun, priyanka, vinayak | 1